## Risk Tracking Template
Risk Tracking Template MAUIS
Date of last review:
ID | Description of Risk | Result of Risk | Impact | Likelihood | Risk Level | Mitigation Strategy | Risk owner | Notes
1 | Users find the app intrusive | Users disincentivised to use the app | High | Medium | High | Positive framing, unintrusive notifications are optional | Dev Team
2 | Complex setup | Users abandon app | High | Low | Medium | Simple onboarding, clear instructions | Design/Dev Team
3 | Users find the app boring | Users abandon app | High | High | High | Engaging design, uncomplicated facts | Design/Dev Team
4 | Confusion around USPs | Users disincentivised to use the app | High | Medium | High | Clear definition of USPs upfront, explained in description and a splashscreen/tutorial page | Design/Dev Team
5 | Data Breach | Exposes personal user data | High | Medium | High | Local storage, end-to-end encyptio, regular security audits | Security Team
6 | Third party analytics SDKs collecting data | Excessive personal data mined | Medium | Medium | Medium | Data processing agreements, minimal data sharing | Dev Team
7 | User data retained beyond necessary periods | Potential violation of GDPR | Medium | Medium | Medium | Automated data deletion, clear retention policies | Legal Team
8 | Accessibility issues | Prevent use by disabled users | Medium | Low | Low | HCI/WCAG compliance, accessibility testing and inclusive design | Design/Dev Team
9 | App crash or freeze | Loss of tracking data | Medium | Medium | Medium | Robust error handling, local data caching and automated backups | Dev Team
10 | Excessive battery drain from continuous use | App is untenable to use | High | High | High | Optimize background processes, efficient data collection algorithms | Dev Team
11 | Incompatibility with OS updates | Core functionality breaking | Hgih | Medium | Hidh | Early beta testing, modular architecture, rapid update cycles | Dev Team
12 | Inaccurate time tracking due to system limits or bugs | Inaccurate data, incorrect app | Mediume | Medium | Medium | Various validation methods, user feedback mechanisms, thorough testing | QA/Dev Team
13 | Scalability issues as user base grows | Unable to handle user traffic | Low | Low | Low | App use and data storage remains local | DevOps
14 | GDPR compliance violations | Leads to fines and loss of customer confidence | High | Medium | High | Design with privacy in mind, follow GDPR practices, Team Training | Legal/Dev Team
15 | App Store violations | Leads to app removal, de-platforming | High | Low | Medium | Review policy regularly, add compliance testing to release pipeline | Legal/Dev Team
16 | Platform specific requirements | Android and iOS app tracking transparency issues | Medium | High | High | Review platform requirements for tracking data, build app consenting to these. | Dev Team
17 | Key Team members sickness | Loss of team momentum | High | High | High | Design documentation for development, clear goals defined and backlog of tasks arranged into sprints | Management
18 | Scope Creep | Goals become diluted with new less necessary tasks, original scope gets pushed back. | Medium | High | High | Clear design documentation, team keeps to Agile principles and Scrum master and Product Owner keep development focussed and a tight feedback loop with stakeholders. | Scrum Master, ProductOwner
19 | Communication breakdown with Forestry | Coordination for the conservation event suffers, brand confidence suffers | High | Medium | High | Written contractual agreements with dates, fallback dates, organisational points of contact and fallback contacts. | Management Legal Team
20 | Users spoof screen time reduction | Unusable data, unachievable costs of conservation to meet spoofed user achievements. | High | Medium | High | Feasible caps for trees planted in an event, logistics for maximum considered and agreed upon in signed documentation. Good faith expectation based on no cash prizes. Daily cap of reduction in-app. | Management Legal & Dev Teams
21 | Loss of data | Forestry team has no data to action conservation event around. | High | Low | Medium | Data is always held on the user device so individual reporting can always be collated into a document and delivered to the Forestry team manually. | Management
22 | Forestry suffers logistics breakdown | Unable to plant trees | High | Low | Medium | Event can be rearranged or replacement materials and equipment used from throughout the organisation. | Forestry/ Management
23 | Adverse weather prevents Forestry event. | Unable to plant trees | Low | Medium | Medium | Events can be rearranged with little issue. Specific dates are not promised but rather are approximate. Users are update with the latest information. | Forestry/ Management
24 | Security vulnerability in the Software Supply Chain | Security vulnerability affects the app, possible malicious code injection | High | Medium | Medium | Integrate Software Bill of Materials (SBOM) software into the CI/CD pipeline like dependency trackers to keep aware of any flagged vulnerabilities in the software supply chain. | Dev and DevOps Team
25

## How to Use this Template
Introduction
A risk tracking template allows you to identify and track any risks that might appear in your project. It's critical to track risks in your projects, so they don't become issues that derail progress. A risk tracking template is a living document, and should be frequently inspected and updated.
Definition of Terms
ID: The identification number of your risk.
Description of Risk: Provide a brief description of your risk that anyone can understand.
Impact: Outline the potential impact that risk can have on your project.
Risk Response: Describe what your reaction to the risk is, in order to quell it.
Risk Level: Define the priority of the risk; how likely it is to affect your project.
Risk Owner: Define the team member or manager in charge of monitoring the risk.
Notes: Add any notes you may have for a better understanding of the risk. Update regularly.